## Sheet1
Task | Start Pts | Pts Done Sprint 1.0 | Pts Done Sprint 1.5 | Pts Done Sprint 2.0 | Pts Done Sprint 2.5 | Pts Done Sprint 3.0 | Pts Done Sprint 3.5 | Pts Done Sprint 4.0 | Pts Done Sprint 4.5 | Total Pts Done
Task 1 | 8 | [8 empty] | 0
Task 2 | 8 | [5 empty] | 5 |  |  | 5
Task 3 | 1 | [8 empty] | 0
Task 4 | 8 |  |  |  | 5 |  |  |  |  | 5
Task 5 | 4 | [8 empty] | 0
Task 6 | 1 | [8 empty] | 0
Task 7 | 6 | 2 | [7 empty] | 2
Task 8 | 1 |  | 1 | [6 empty] | 1
Task 9 | 3 |  |  | 3 | [5 empty] | 3
Task 10 | 1 | [8 empty] | 0
Actual Remaining Effort | 41 | 39 | 38 | 35 | 30 | 30 | 25 | 25 | 25
Estimated Remaining Effort | 41 | 35.875 | 30.75 | 25.625 | 20.5 | 15.375 | 10.25 | 5.125 | 0